## Master Division Overview
DIVISION INCEPTION MASTER EXECUTIVE OVERVIEW
Division Filter: | Divisi RKA |  | Squad Filter: | All Squads |  |  | Export Date: | 04 Aug 2026 08:49
Total Inceptions: | 6
# | Project Name | Division | Squad | Planned Start | Target End | Actual Start | Actual End | Schedule Status | Total Mandays | Activities | Assigned PICs | Notes
1 | Penyesuaian Otomatisasi Data Hasil Putusan Komite Kredit | Divisi RKA | Squad MIS | 21 Jul 2026 | 22 Oct 2026 | 29 Jul 2026 | - | On Track | 66 | 6 | Unassigned | Start Date 21/7 Deploy Date 7/10
2 | Pengembangan Menu MIS Kualitas Kredit versi REK, Jenis Transaksi UP KCA RAHN 2026, dan Tambah Kolom SL Gadai Bermasalah | Divisi RKA | Squad MIS | 28 Jul 2026 | 22 Oct 2026 | 28 Jul 2026 | 03 Aug 2026 | On Track | 61 | 6 | Unassigned
3 | Pegasus Phase Improvement | Divisi RKA | Squad Asuransi | 07 Jul 2026 | 20 Nov 2026 | 07 Jul 2026 | - | On Track | 130 | 7 | Unassigned
4 | Pengembangan dan Perbaikan PACS III Fase 1 | Divisi RKA | Squad RKA | 10 Jul 2026 | 04 Nov 2026 | 10 Jul 2026 | 23 Jul 2026 | On Track | 82 | 7 | Unassigned
5 | Pengembangan Modul Ekstra Diskon Pelunasan Produk Pinjaman Modal Produktif (PMP) untuk Kredit Aktif, PYD DPP dan Hapus Buku | Divisi RKA | Pooling Core | 28 Jul 2026 | 22 Jan 2027 | 28 Jul 2026 | - | On Track | 125 | 8 | Unassigned
6 | Improvement Dashboard Monev Credit Scoring | Divisi RKA | Squad Big Data | 20 Jul 2026 | 20 Nov 2026 | 20 Jul 2026 | 28 Jul 2026 | On Track | 105 | 10 | Unassigned
TOTAL

## Squad MIS Summary
PROJECT SCHEDULE SUMMARY REPORT
Project Name: | Penyesuaian Otomatisasi Data Hasil Putusan Komite Kredit |  |  |  | Start Date: | 21 Jul 2026
Division: | Divisi RKA |  |  |  | Squad: | Squad MIS
Notes: | Start Date 21/7 Deploy Date 7/10
# | Activity Name | Mandays | Start Dependency | Planned Start | Planned End | Actual Start | Actual End | PIC / Lead | Remarks
1 | GCanvas | 10 | Project Start Date | 21 Jul 2026 | 03 Aug 2026 | 29 Jul 2026 | - | - | Estimasi tgl 7 Agustus done
2 | Development MIS | 20 | After Previous Ends | 04 Aug 2026 | 02 Sep 2026 | - | - | - | -
3 | SIT | 20 | After Previous Ends | 03 Sep 2026 | 30 Sep 2026 | - | - | - | -
4 | UAT | 1 | After Previous Ends | 01 Oct 2026 | 01 Oct 2026 | - | - | - | -
5 | Deployment | 4 | After Previous Ends | 02 Oct 2026 | 07 Oct 2026 | - | - | - | -
6 | Post Implementation Review | 11 | After Previous Ends | 08 Oct 2026 | 22 Oct 2026 | - | - | - | Scope Medium : 15 Hari Calendar
Total
PROJECT SCHEDULE SUMMARY REPORT
Project Name: | Pengembangan Menu MIS Kualitas Kredit versi REK, Jenis Transaksi UP KCA RAHN 2026, dan Tambah Kolom SL Gadai Bermasalah |  |  |  | Start Date: | 28 Jul 2026
Division: | Divisi RKA |  |  |  | Squad: | Squad MIS
Notes: | None
# | Activity Name | Mandays | Start Dependency | Planned Start | Planned End | Actual Start | Actual End | PIC / Lead | Remarks
1 | Requirement Gathering | 5 | Project Start Date | 28 Jul 2026 | 03 Aug 2026 | 28 Jul 2026 | 03 Aug 2026 | - | Rizki Sugiharto
2 | Development MIS | 20 | After Previous Ends | 04 Aug 2026 | 02 Sep 2026 | 04 Aug 2026 | - | - | F. Dhemas Angger
3 | SIT | 15 | After Previous Ends | 03 Sep 2026 | 23 Sep 2026 | - | - | - | Salma Nida
4 | UAT | 5 | After Previous Ends | 24 Sep 2026 | 30 Sep 2026 | - | - | - | Salma Nida
5 | Deployment | 5 | After Previous Ends | 01 Oct 2026 | 07 Oct 2026 | - | - | - | -
6 | Post Implementation Review | 11 | After Previous Ends | 08 Oct 2026 | 22 Oct 2026 | - | - | - | Scope Medium : 15 Hari Kalender
Total

## Gantt Squad MIS
Activity | Start Date | End Date | PIC / Lead | Mandays | July 2026 | [30 empty] | August 2026 | [30 empty] | September 2026 | [29 empty] | October 2026 | [30 empty] | November 2026
[5 empty] | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5
PROJECT: PENYESUAIAN OTOMATISASI DATA HASIL PUTUSAN KOMITE KREDIT
GCanvas | 21 Jul 2026 | 03 Aug 2026 | - | 10 | July 2026 Mo 27: 10d
Development MIS | 04 Aug 2026 | 02 Sep 2026 | - | 20 | August 2026 Tu 18: 20d
SIT | 03 Sep 2026 | 30 Sep 2026 | - | 20 | September 2026 We 16: 20d
UAT | 01 Oct 2026 | 01 Oct 2026 | - | 1 | bar: October 2026 Th 1
Deployment | 02 Oct 2026 | 07 Oct 2026 | - | 4 | bar: October 2026 Fr 2; October 2026 Mo 5 to October 2026 We 7
Post Implementation Review | 08 Oct 2026 | 22 Oct 2026 | - | 11 | October 2026 Th 15: 11d
PROJECT: PENGEMBANGAN MENU MIS KUALITAS KREDIT VERSI REK, JENIS TRANSAKSI UP KCA RAHN 2026, DAN TAMBAH KOLOM SL GADAI BERMASALAH
Requirement Gathering | 28 Jul 2026 | 03 Aug 2026 | - | 5 | bar: July 2026 Tu 28 to July 2026 Fr 31; August 2026 Mo 3
Development MIS | 04 Aug 2026 | 02 Sep 2026 | - | 20 | August 2026 Tu 18: 20d
SIT | 03 Sep 2026 | 23 Sep 2026 | - | 15 | bar: September 2026 Th 3 to September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11; September 2026 Mo 14 to September 2026 Fr 18; September 2026 Mo 21 to September 2026 We 23
UAT | 24 Sep 2026 | 30 Sep 2026 | - | 5 | bar: September 2026 Th 24 to September 2026 Fr 25; September 2026 Mo 28 to September 2026 We 30
Deployment | 01 Oct 2026 | 07 Oct 2026 | - | 5 | bar: October 2026 Th 1 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 We 7
Post Implementation Review | 08 Oct 2026 | 22 Oct 2026 | - | 11 | October 2026 Th 15: 11d

## Squad Asuransi Summary
PROJECT SCHEDULE SUMMARY REPORT
Project Name: | Pegasus Phase Improvement |  |  |  | Start Date: | 07 Jul 2026
Division: | Divisi RKA |  |  |  | Squad: | Squad Asuransi
Notes: | None
# | Activity Name | Mandays | Start Dependency | Planned Start | Planned End | Actual Start | Actual End | PIC / Lead | Remarks
1 | GCanvas | 21 | Project Start Date | 07 Jul 2026 | 04 Aug 2026 | 07 Jul 2026 | - | - | -
2 | Development Core | 31 | Same Time as Previous | 07 Jul 2026 | 19 Aug 2026 | 07 Jul 2026 | - | - | -
3 | SIT | 41 | Manual Specific Date | 03 Aug 2026 | 30 Sep 2026 | - | - | - | -
4 | UAT + Fixing | 7 | After Previous Ends | 01 Oct 2026 | 09 Oct 2026 | - | - | - | -
5 | Regression | 6 | After Previous Ends | 12 Oct 2026 | 19 Oct 2026 | - | - | - | -
6 | Deployment | 11 | After Previous Ends | 20 Oct 2026 | 03 Nov 2026 | - | - | - | -
7 | Post Implementation Review | 13 | After Previous Ends | 04 Nov 2026 | 20 Nov 2026 | - | - | - | -
Total

## Gantt Squad Asuransi
Activity | Start Date | End Date | PIC / Lead | Mandays | July 2026 | [30 empty] | August 2026 | [30 empty] | September 2026 | [29 empty] | October 2026 | [30 empty] | November 2026 | [29 empty] | December 2026
[5 empty] | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4
PROJECT: PEGASUS PHASE IMPROVEMENT
GCanvas | 07 Jul 2026 | 04 Aug 2026 | - | 21 | July 2026 Tu 21: 21d
Development Core | 07 Jul 2026 | 19 Aug 2026 | - | 31 | July 2026 Tu 28: 31d
SIT | 03 Aug 2026 | 30 Sep 2026 | - | 41 | September 2026 Tu 1: 41d
UAT + Fixing | 01 Oct 2026 | 09 Oct 2026 | - | 7 | bar: October 2026 Th 1 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 Fr 9
Regression | 12 Oct 2026 | 19 Oct 2026 | - | 6 | bar: October 2026 Mo 12 to October 2026 Fr 16; October 2026 Mo 19
Deployment | 20 Oct 2026 | 03 Nov 2026 | - | 11 | October 2026 Tu 27: 11d
Post Implementation Review | 04 Nov 2026 | 20 Nov 2026 | - | 13 | November 2026 Th 12: 13d

## Squad RKA Summary
PROJECT SCHEDULE SUMMARY REPORT
Project Name: | Pengembangan dan Perbaikan PACS III Fase 1 |  |  |  | Start Date: | 10 Jul 2026
Division: | Divisi RKA |  |  |  | Squad: | Squad RKA
Notes: | None
# | Activity Name | Mandays | Start Dependency | Planned Start | Planned End | Actual Start | Actual End | PIC / Lead | Remarks
1 | Requirement Gathering | 10 | Project Start Date | 10 Jul 2026 | 23 Jul 2026 | 10 Jul 2026 | 23 Jul 2026 | - | -
2 | Development Core | 20 | After Previous Ends | 24 Jul 2026 | 21 Aug 2026 | 24 Jul 2026 | - | - | -
3 | SIT | 25 | After Previous Ends | 24 Aug 2026 | 28 Sep 2026 | - | - | - | -
4 | UAT | 2 | After Previous Ends | 29 Sep 2026 | 30 Sep 2026 | - | - | - | -
5 | Regression | 5 | After Previous Ends | 01 Oct 2026 | 07 Oct 2026 | - | - | - | -
6 | Deployment | 5 | After Previous Ends | 08 Oct 2026 | 14 Oct 2026 | - | - | - | -
7 | Post Implementation Review | 15 | After Previous Ends | 15 Oct 2026 | 04 Nov 2026 | - | - | - | -
Total

## Gantt Squad RKA
Activity | Start Date | End Date | PIC / Lead | Mandays | July 2026 | [30 empty] | August 2026 | [30 empty] | September 2026 | [29 empty] | October 2026 | [30 empty] | November 2026
[5 empty] | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
PROJECT: PENGEMBANGAN DAN PERBAIKAN PACS III FASE 1
Requirement Gathering | 10 Jul 2026 | 23 Jul 2026 | - | 10 | July 2026 Th 16: 10d
Development Core | 24 Jul 2026 | 21 Aug 2026 | - | 20 | August 2026 Fr 7: 20d
SIT | 24 Aug 2026 | 28 Sep 2026 | - | 25 | September 2026 Th 10: 25d
UAT | 29 Sep 2026 | 30 Sep 2026 | - | 2 | bar: September 2026 Tu 29 to September 2026 We 30
Regression | 01 Oct 2026 | 07 Oct 2026 | - | 5 | bar: October 2026 Th 1 to October 2026 Fr 2; October 2026 Mo 5 to October 2026 We 7
Deployment | 08 Oct 2026 | 14 Oct 2026 | - | 5 | bar: October 2026 Th 8 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 We 14
Post Implementation Review | 15 Oct 2026 | 04 Nov 2026 | - | 15 | bar: October 2026 Th 15 to October 2026 Fr 16; October 2026 Mo 19 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 We 4

## Pooling Core Summary
PROJECT SCHEDULE SUMMARY REPORT
Project Name: | Pengembangan Modul Ekstra Diskon Pelunasan Produk Pinjaman Modal Produktif (PMP) untuk Kredit Aktif, PYD DPP dan Hapus Buku |  |  |  | Start Date: | 28 Jul 2026
Division: | Divisi RKA |  |  |  | Squad: | Pooling Core
Notes: | None
# | Activity Name | Mandays | Start Dependency | Planned Start | Planned End | Actual Start | Actual End | PIC / Lead | Remarks
1 | Requirement Gathering | 10 | Project Start Date | 28 Jul 2026 | 10 Aug 2026 | 28 Jul 2026 | - | - | Febry Eka Putra
2 | Development Core | 39 | After Previous Ends | 11 Aug 2026 | 06 Oct 2026 | - | - | - | TBC
3 | Development Middleware | 7 | After Previous Ends | 07 Oct 2026 | 15 Oct 2026 | - | - | - | -
4 | SIT | 30 | After Previous Ends | 16 Oct 2026 | 26 Nov 2026 | - | - | - | Islach/Icha
5 | UAT | 3 | After Previous Ends | 27 Nov 2026 | 01 Dec 2026 | - | - | - | Islach/Icha
6 | Regression | 10 | After Previous Ends | 02 Dec 2026 | 15 Dec 2026 | - | - | - | Islach/Icha
7 | Deployment | 5 | After Previous Ends | 16 Dec 2026 | 22 Dec 2026 | - | - | - | -
8 | Post Implementation Review | 21 | After Previous Ends | 23 Dec 2026 | 22 Jan 2027 | - | - | - | Scope High : 30 Mandays PIR
Total

## Gantt Pooling Core
Activity | Start Date | End Date | PIC / Lead | Mandays | July 2026 | [30 empty] | August 2026 | [30 empty] | September 2026 | [29 empty] | October 2026 | [30 empty] | November 2026 | [29 empty] | December 2026 | [30 empty] | January 2027
[5 empty] | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
PROJECT: PENGEMBANGAN MODUL EKSTRA DISKON PELUNASAN PRODUK PINJAMAN MODAL PRODUKTIF (PMP) UNTUK KREDIT AKTIF, PYD DPP DAN HAPUS BUKU
Requirement Gathering | 28 Jul 2026 | 10 Aug 2026 | - | 10 | August 2026 Mo 3: 10d
Development Core | 11 Aug 2026 | 06 Oct 2026 | - | 39 | September 2026 Tu 8: 39d
Development Middleware | 07 Oct 2026 | 15 Oct 2026 | - | 7 | bar: October 2026 We 7 to October 2026 Fr 9; October 2026 Mo 12 to October 2026 Th 15
SIT | 16 Oct 2026 | 26 Nov 2026 | - | 30 | November 2026 Th 5: 30d
UAT | 27 Nov 2026 | 01 Dec 2026 | - | 3 | bar: November 2026 Fr 27; November 2026 Mo 30 to December 2026 Tu 1
Regression | 02 Dec 2026 | 15 Dec 2026 | - | 10 | December 2026 Tu 8: 10d
Deployment | 16 Dec 2026 | 22 Dec 2026 | - | 5 | bar: December 2026 We 16 to December 2026 Fr 18; December 2026 Mo 21 to December 2026 Tu 22
Post Implementation Review | 23 Dec 2026 | 22 Jan 2027 | - | 21 | January 2027 Th 7: 21d

## Squad Big Data Summary
PROJECT SCHEDULE SUMMARY REPORT
Project Name: | Improvement Dashboard Monev Credit Scoring |  |  |  | Start Date: | 20 Jul 2026
Division: | Divisi RKA |  |  |  | Squad: | Squad Big Data
Notes: | None
# | Activity Name | Mandays | Start Dependency | Planned Start | Planned End | Actual Start | Actual End | PIC / Lead | Remarks
1 | Requirement Gathering | 6 | Project Start Date | 20 Jul 2026 | 27 Jul 2026 | 20 Jul 2026 | 28 Jul 2026 | - | -
2 | Development Overview (workflow, pengajuan, kredit mikro) | 11 | Manual Specific Date | 13 Jul 2026 | 27 Jul 2026 | - | - | - | -
3 | Development Monev Credit Scoring CSI PSI | 26 | After Previous Ends | 28 Jul 2026 | 03 Sep 2026 | - | - | - | -
4 | Development Data Nilai AUC dan Confussion | 6 | After Previous Ends | 04 Sep 2026 | 11 Sep 2026 | - | - | - | -
5 | Development NPL Kredit | 11 | After Previous Ends | 14 Sep 2026 | 28 Sep 2026 | - | - | - | -
6 | SIT | 16 | After Previous Ends | 29 Sep 2026 | 20 Oct 2026 | - | - | - | -
7 | UAT + Fixing | 6 | After Previous Ends | 21 Oct 2026 | 28 Oct 2026 | - | - | - | -
8 | Prepare Deploy | 6 | After Previous Ends | 29 Oct 2026 | 05 Nov 2026 | - | - | - | -
9 | Deployment | 6 | Same Time as Previous | 29 Oct 2026 | 05 Nov 2026 | - | - | - | -
10 | PIR + Kelengkapan SEO | 11 | After Previous Ends | 06 Nov 2026 | 20 Nov 2026 | - | - | - | -
Total

## Gantt Squad Big Data
Activity | Start Date | End Date | PIC / Lead | Mandays | July 2026 | [30 empty] | August 2026 | [30 empty] | September 2026 | [29 empty] | October 2026 | [30 empty] | November 2026 | [29 empty] | December 2026
[5 empty] | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4
PROJECT: IMPROVEMENT DASHBOARD MONEV CREDIT SCORING
Requirement Gathering | 20 Jul 2026 | 27 Jul 2026 | - | 6 | bar: July 2026 Mo 20 to July 2026 Fr 24; July 2026 Mo 27
Development Overview (workflow, pengajuan, kredit mikro) | 13 Jul 2026 | 27 Jul 2026 | - | 11 | July 2026 Mo 20: 11d
Development Monev Credit Scoring CSI PSI | 28 Jul 2026 | 03 Sep 2026 | - | 26 | bar: July 2026 Tu 28 to July 2026 Fr 31; August 2026 Mo 3 to August 2026 Fr 7; August 2026 Mo 10 to August 2026 Fr 14; August 2026 Tu 18 to August 2026 Fr 21; August 2026 Mo 24; August 2026 We 26 to August 2026 Fr 28; August 2026 Mo 31 to September 2026 Th 3
Development Data Nilai AUC dan Confussion | 04 Sep 2026 | 11 Sep 2026 | - | 6 | bar: September 2026 Fr 4; September 2026 Mo 7 to September 2026 Fr 11
Development NPL Kredit | 14 Sep 2026 | 28 Sep 2026 | - | 11 | September 2026 Mo 21: 11d
SIT | 29 Sep 2026 | 20 Oct 2026 | - | 16 | October 2026 Fr 9: 16d
UAT + Fixing | 21 Oct 2026 | 28 Oct 2026 | - | 6 | bar: October 2026 We 21 to October 2026 Fr 23; October 2026 Mo 26 to October 2026 We 28
Prepare Deploy | 29 Oct 2026 | 05 Nov 2026 | - | 6 | bar: October 2026 Th 29 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Th 5
Deployment | 29 Oct 2026 | 05 Nov 2026 | - | 6 | bar: October 2026 Th 29 to October 2026 Fr 30; November 2026 Mo 2 to November 2026 Th 5
PIR + Kelengkapan SEO | 06 Nov 2026 | 20 Nov 2026 | - | 11 | November 2026 Fr 13: 11d