## Squad MIS Summary
PROJECT SCHEDULE SUMMARY REPORT
Project Name: | Pengembangan Menu MIS Kualitas Kredit versi REK, Jenis Transaksi UP KCA RAHN 2026, dan Tambah Kolom SL Gadai Bermasalah |  |  |  | Start Date: | 28 Jul 2026
Division: | Divisi RKA |  |  |  | Squad: | Squad MIS
Notes: | None
# | Activity Name | Mandays | Start Dependency | Start Date | End Date | Remarks
1 | Requirement Gathering | 5 | Project Start Date | 28 Jul 2026 | 03 Aug 2026 | RIZKI SUGIHARTO
2 | Development MIS | 20 | After Previous Ends | 04 Aug 2026 | 02 Sep 2026 | FRANCISKUS DHEMAS ANGGER
3 | SIT | 15 | After Previous Ends | 03 Sep 2026 | 23 Sep 2026 | Salma Nida Khofiyya
4 | UAT | 5 | After Previous Ends | 24 Sep 2026 | 30 Sep 2026 | Salma Nida Khofiyya
5 | Deployment | 5 | After Previous Ends | 01 Oct 2026 | 07 Oct 2026 | -
6 | Post Implementation Review | 11 | After Previous Ends | 08 Oct 2026 | 22 Oct 2026 | Scope Medium : 15 Hari Kalender
Total |  | 61
PROJECT SCHEDULE SUMMARY REPORT
Project Name: | Penyesuaian Otomatisasi Data Hasil Putusan Komite Kredit |  |  |  | Start Date: | 21 Jul 2026
Division: | Divisi RKA |  |  |  | Squad: | Squad MIS
Notes: | Start Date 21/7 Deploy Date 7/10
# | Activity Name | Mandays | Start Dependency | Start Date | End Date | Remarks
1 | GCanvas | 10 | Project Start Date | 21 Jul 2026 | 03 Aug 2026 | Andri Pratama
2 | Development MIS | 20 | After Previous Ends | 04 Aug 2026 | 02 Sep 2026 | NAUFAL EKA SULAEMAN
3 | SIT | 20 | After Previous Ends | 03 Sep 2026 | 30 Sep 2026 | -
4 | UAT | 1 | After Previous Ends | 01 Oct 2026 | 01 Oct 2026 | -
5 | Deployment | 4 | After Previous Ends | 02 Oct 2026 | 07 Oct 2026 | -
6 | Post Implementation Review | 11 | After Previous Ends | 08 Oct 2026 | 22 Oct 2026 | Scope Medium : 15 Hari Calendar
Total |  | 66

## Gantt Squad MIS
Activity | Start Date | End Date | Mandays | 2026-07-01 | [10 empty] | August 2026 | [30 empty] | September 2026 | [29 empty] | October 2026
|  |  |  | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  |  |  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Requirement Gathering | 28 Jul 2026 | 03 Aug 2026 | 5 | bar: 2026-07-01 Tu 28 to August 2026 Mo 3
Development MIS | 04 Aug 2026 | 02 Sep 2026 | 20 | August 2026 Tu 18: 20d
SIT | 03 Sep 2026 | 23 Sep 2026 | 15 | September 2026 Su 13: 15d
UAT | 24 Sep 2026 | 30 Sep 2026 | 5 | bar: September 2026 Th 24 to September 2026 We 30
Deployment | 01 Oct 2026 | 07 Oct 2026 | 5 | bar: October 2026 Th 1 to October 2026 We 7
Post Implementation Review | 08 Oct 2026 | 22 Oct 2026 | 11 | October 2026 Th 15: 11d
Activity | Start Date | End Date | Mandays | 2026-07-01 Tu 21: 2026-07-01; August 2026 Sa 1: August 2026; September 2026 Tu 1: September 2026; October 2026 Th 1: October 2026
|  |  |  | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
|  |  |  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
GCanvas | 21 Jul 2026 | 03 Aug 2026 | 10 | 2026-07-01 Mo 27: 10d
Development MIS | 04 Aug 2026 | 02 Sep 2026 | 20 | August 2026 Tu 18: 20d
SIT | 03 Sep 2026 | 30 Sep 2026 | 20 | September 2026 We 16: 20d
UAT | 01 Oct 2026 | 01 Oct 2026 | 1 | bar: 2026-07-01 Sa 25 to 2026-07-01 Su 26; October 2026 Th 1
Deployment | 02 Oct 2026 | 07 Oct 2026 | 4 | bar: 2026-07-01 Sa 25 to 2026-07-01 Su 26; October 2026 Fr 2 to October 2026 We 7
Post Implementation Review | 08 Oct 2026 | 22 Oct 2026 | 11 | October 2026 Th 15: 11d

## Pooling Core Summary
PROJECT SCHEDULE SUMMARY REPORT
Project Name: | Pengembangan Modul Ekstra Diskon Pelunasan Produk Pinjaman Modal Produktif (PMP) untuk Kredit Aktif, PYD DPP dan Hapus Buku |  |  |  | Start Date: | 28 Jul 2026
Division: | Divisi RKA |  |  |  | Squad: | Pooling Core
Notes: | None
# | Activity Name | Mandays | Start Dependency | Start Date | End Date | Remarks
1 | Requirement Gathering | 10 | Project Start Date | 28 Jul 2026 | 10 Aug 2026 | Febry Eka Putra
2 | Development Core | 39 | After Previous Ends | 11 Aug 2026 | 06 Oct 2026 | Moh Fajar Alfarizy, Wachid
3 | SIT | 30 | After Previous Ends | 07 Oct 2026 | 17 Nov 2026 | Islach/Icha
4 | UAT | 3 | After Previous Ends | 18 Nov 2026 | 20 Nov 2026 | Islach/Icha
5 | Regression | 10 | After Previous Ends | 23 Nov 2026 | 04 Dec 2026 | Islach/Icha
6 | Deployment | 5 | After Previous Ends | 07 Dec 2026 | 11 Dec 2026 | -
7 | Post Implementation Review | 21 | After Previous Ends | 14 Dec 2026 | 13 Jan 2027 | Scope High : 30 Mandays PIR
Total |  | 118

## Gantt Pooling Core
Activity | Start Date | End Date | Mandays | 2026-07-01 |  |  |  | August 2026 | [30 empty] | September 2026 | [29 empty] | October 2026 | [30 empty] | November 2026 | [29 empty] | December 2026 | [30 empty] | January 2027
|  |  |  | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su
|  |  |  | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Requirement Gathering | 28 Jul 2026 | 10 Aug 2026 | 10 | August 2026 Mo 3: 10d
Development Core | 11 Aug 2026 | 06 Oct 2026 | 39 | September 2026 Tu 8: 39d
SIT | 07 Oct 2026 | 17 Nov 2026 | 30 | October 2026 Tu 27: 30d
UAT | 18 Nov 2026 | 20 Nov 2026 | 3 | bar: November 2026 We 18 to November 2026 Fr 20
Regression | 23 Nov 2026 | 04 Dec 2026 | 10 | November 2026 Sa 28: 10d
Deployment | 07 Dec 2026 | 11 Dec 2026 | 5 | bar: December 2026 Mo 7 to December 2026 Fr 11
Post Implementation Review | 14 Dec 2026 | 13 Jan 2027 | 21 | December 2026 Tu 29: 21d